## Sheet1
10-Year Bridge, Culvert & Storm Sewer Plan
location | project | priority
Adair Drive | extend storm sewer installation * | 1
Bean Road, Berks to Beyer | reconstruct downstream headwall | 1
Bean Road, Whitehall to North Wales | patch abutment (masonry) | 1
| backfill scour * | 2
Grange Avenue, Mill to Water Street | remove sediment | 2
Green Hill Road | replace culvert, install inlet box * | 1
Green Hill Road, Kriebel Mill to Anders (N) | underpin culvert | 2
Heebner Road, Hollow to Kriebel Mill | repair wing wall (masonry) | 1
| install rock protection, backfill scour, replace/repair timbers | 2
Hickory Hill Drive, Valley Forge to Landis | install rock protection, remove sediment deposition, install standard bridge railing | 2
Hollow Road, Doe Brook to Fawn | backfill scour * | 2
Hollow Road, Fawn to Zacharias | reseal deck joints | 2
Hollow Road, Stump Hall to Heebner Road (N) | replace steel pipe culvert | 1
| backfill scour | 2
Hollow Road, Stump Hall to Heebner (S) | underpin abutment | 1
Hollow Road, Zacharias to Deer Creek | install scour protection * | 1
| patch superstructure, remove sediment | 2
Kriebel Mill Road, Water Street to Custer | install rock protection, remove sediment | 2
* in proposed 2021 Budget
10-Year Bridge, Culvert & Storm Sewer Plan
location | project | priority
Kriebel Mill Road, Stump to Water Street | install guardrails * | 1
Kriebel Mill Road, Water Street to Hedwig | underpin abutment | 1
| install rock protection, repair curb and headwalls | 2
Kriebel Mill Road, Water Street to Mill | road closure assessment | 2
Landis Road, Hickory Hill to Potshop | install rock protection, remove sediment | 2
Mill Road, Merrybrook to Hollow | repoint superstructure, remove sediment | 2
Mill Road, at Merrybrook | install guardrails * | 1
Spring Hill Road, Trooper to Reiner | remove sediment | 2
Weber Road, Skippack to Curtis | repair structure (masonry), install bridge railing | 1
| patch underside of structure, backfill scour, install rock protection | 2
Wentz Church Road, Skippack to Barley | underpin abutment, install rock protection | 2
* in proposed 2021 Budget
Please note… The above lists are subject to change. Worcester Township continuously reviews its bridges, culverts and storm sewer system, and prioritizes improvements as conditions warrant.